## Slide 1: <Agency>’s TechStat Framework
<Date>
Agency Seal

## Slide 2: Agenda
TechStat Overview
TechStat Process
Managing Outcomes

## Slide 3: TechStat Overview
What is a TechStat?
TechStat is a face-to-face, evidence-based accountability review of an IT investment
TechStat results in concrete actions to address weaknesses
TechStat reduces wasteful spending by turning around troubled programs and
terminating failed programs sooner
TechStat Is: | TechStat is Not:
Actionable: participants should leave the session armed with next steps to improve outcomes | Routine: sessions should not be used for routine, small impact change requests
A Spotlight: sessions should highlight problems areas and focus deeply on pain points | Comprehensive: not an IV&V, IBR, PIR (though these could be inputs or requested actions of a TechStat)
Prescriptive: sessions should be limited to 60 minutes and result in clear actions, with owners and deadlines | One-Size-Fits-All: the roles and responsibilities of the CIO, IRB, and TechStat will vary by agency
A Tool: sessions should be used when executive level influence is needed | A Review: sessions should not be used for cyclical control reviews (“business as usual”)

## Slide 4: TechStat Implementation Requires Organizational Change
Training
  Leadership
  Project and Program Staff
Governance
  Revised Investment Review Board Charter
Amended Roles and Responsibilities
  TechStat team, CIO, Investment Manager, Business Owner, IRB
TechStat Overview
Notes: 4

## Slide 5
TechStat Analysis Outcomes:
  Questions and information requests for the investment being reviewed
  TechStat thesis - discovered through analysis of the investment documentation requested
  Briefing deck for the IRB that highlights key issues needing resolution
  Additional outputs as requested by the agency CIO
5
 | Initial Baseline Review | Control Review | Rebaseline Request Review
Applicable Investment Lifecycle | Planning Development | Development Mixed Lifecycle | Development Mixed Lifecycle
Goals | Verify the technical content of the Performance Measurement Baseline Review and assess both resource and schedule estimates Identify potential risks | Provide a systematic assessment of the investment’s current state Identify any new risks and changes in scope since prior review | Review and redefine project baselines that are affected by a significant change in project goals Reconsider baselines that are no longer useful as a management tool
TechStat Analysis (by Investment Lifecycle)
TechStat Overview (continued)
Notes: 5
5

## Slide 6: TechStat Process
1. Discovery
4. TechStat Facilitation
5. Follow-up
2. Analysis
3. Preparation
1.1 Identify Investment for Review
1.2 Notify Investment Manager and Business Owner
2.1 Collect Investment Documentation
2.2. Engage Subject Matter Experts
3.2 Prepare Executive Briefing
3.1 Invite Relevant Attendees
2.3 Formulate Thesis, Validate Facts and Synthesize Analysis
3.3. Complete Administrative and Logistics Support
3.4 Pre-Brief CIO
4. TechStat Facilitation - Record Action Items with Owners and Timelines
5.1 Distribute Memo of Record
5.2 Enter and Track Action Items to Conclusion in Repository
5.3 Incorporate Lessons Learned in Enterprise
High-Level Process

## Slide 7: Roles and Responsibilities
Responsibility | TechStat (CPIC) Team | CIO | Investment / Project Manager | Business Owner | IRB Chair | IRB Membership
Identify investments for TechStat | Primary | X |  |  |  | X
Lead the documentation review, perform critical analysis, and provide briefing materials to the IRB prior to the meeting | Primary |  |  |  |  | 
Support documentation review | Primary | X |  |  |  | X
Track and monitor action items resulting from TechStats | Primary |  |  |  |  | 
Brief leadership (CIO, etc.) prior to the meeting | Primary |  | X | X |  | 
Provide full and complete documentation to support a given review |  |  | Primary | X |  | 
Coordinate staffing necessary to support a review |  | Primary |  |  |  | 
Execute Action Plan resulting from TechStat Reviews |  |  | Primary | X |  | 
Present findings to IRB | Primary |  | X |  |  | 
Coordinate and facilitate TechStat meeting | Primary |  |  |  |  | 
Lead TechStat meeting and ask probing questions |  | Primary |  |  | X | 
Provide expert advice and objective recommendations that assist the IRB in decision-making | X | X |  |  |  | 
Ensures decisions are consistent with the Agency and IT strategic plans, policies and guidelines |  | X |  |  | X | 
Notify Investment of TechStat | Primary |  |  |  |  | 
Document decisions and action plan resulting from TechStat | Primary |  |  |  |  | 
Attend TechStat and contribute to group decisions | X | X | X | X | X | X
TechStat Process

## Slide 8: Day of TechStat
Roles
  CIO and IRB Co-Chair will chair the meeting
  TechStat team lead will facilitate
  Investment Manager will serve as primary respondent
Format (Structured 1 hour meeting)
  10 minute briefing on issues and challenges
  40 minute discussion of root causes and potential corrective actions
  10 minute decisions on corrective action items
8
TechStat Process
Notes: 8
8

## Slide 9: Managing Outcomes
Potential Outcomes
  Continue as planned with minor recovery and corrective action plans;
  Continue with modifications such as:
    Rescope and rebaseline,
    Reassess make/buy approach,
    Reassign project team and/or vendor,
    Implement extensive corrective action plans,
    Thorough root cause analysis of performance issues;
  Halt investment and:
    Determine if the project is still necessary,
    Recharter – agency performs a deeper analysis of the program,
    Stabilize the application to a point of non-impact to users and business operations.
Managing Action Items
Incorporating Lessons Learned